## Dashboard
Dashboard de Acompanhamento de Tarefas
Progresso Geral: | 43.33%
Tarefas Fechadas: | 39
Total de Tarefas: | 90
GROUP | SEQ | DESCRIPTION | STATUS | EXTERNAL TASK | ORIG
Planned | 1 | 24-23-00-004 - RAM AIR TURBINE (RAT) GENERATOR Functional Check of RAT Generator System for proper voltage and frequency. Check RAT manual and automatic deploy. PN:1703781A, SN: 0767 | CLOSED | 24-23-00-004
Planned | 2 | 24-23-00-004C - RAM AIR TURBINE (RAT) GENERATOR Functional Check of RAT Generator System for proper voltage and frequency. Check RAT manual and automatic deploy. PN:1703781A, SN: 0767 | CLOSED | 24-23-00-004C
Planned | 3 | 33-50-01-001 - EMERGENCY-LIGHT POWER UNIT - FUNCTIONAL TEST. #01 FWD PN: 3400-22-10, SN: 010533 #02 FWD PN: 3400-22-10, SN: 010472 #LH REAR PN: 3400-22-10, SN: 010437 #RH REAR PN: 3400-22-10, SN: 013002 #RH CENT PN: 3400-22-10, SN: 001642 #LH | CLOSED | 33-50-01-001
Planned | 4 | 33-51-01-002 - FLASHLIGHT Inspect (General Visual) Flashlight and Recharging Bracket. #1 P2-07-0009-520 LOTE: C020028392 #2 P2-07-0009-520LOTE: C02028392 #3 P2-07-0009-520 LOTE: C02028392 #4 P2-07-0009-520 LOTE: C02000400 #5 P2-07-0009-520 L | CLOSED | 33-51-01-002
Planned | 5 | 33-51-01-001 - FLASHLIGHT - RESTORATION OF FLASHLIGHT BATTERY NOTE: ON ACFT WITH RECHARGEABLE FLASHLIGHT #1 P2- 07-0009-520 LOTE: C020028392 #2 P2-07-0009-520 LOTE: C02028392 #3 P2-07-0009-520 LOTE: C02028392 #4 P2-07-0009-520 LOTE: C02000400 | CLOSED | 33-51-01-001
Planned | 6 | 25-62-03-001 - DISCARD OF MEGAPHONE BATTERIES. NOTE: BOTH MEGAPHONES - LH STOWAGE AND AFT RH WINDSCREEN. PN:ACR/EM-1A, SN:41904 | CLOSED | 25-62-03-001
Planned | 7 | COMPLY WITH GE LMM 78-30-00-800- 807 - THRUST REVERSER TRACK LINER LUBRICATION LH AND RH. GROUP DESCRIPTION STATUS EXTERNAL TASK ORIG | CLOSED | GE LMM 78-30-00-800-807
Planned | 8 | 28-11-00-003 - FUEL TANK BIOCIDE APPLICATION Servicing of Fuel Tank (Biocide application). Apply biocide to avoid microbiological contamination. | OPEN | 28-11-00-003
Planned | 9 | 28-11-00-002 - FUEL TANK DRAINED WATER - FUNCTIONAL CHECK OF FUEL TANK DRAINED WATER. CHECK FOR PRESENCE OF MICROBIOLOGICAL CONTAMINATION. | CLOSED | 28-11-00-002
Planned | 10 | 38-31-00-001 - GRAY WATER LINES Flush of Gray Water Lines. | CLOSED | 38-31-00-001
Planned | 11 | 38-11-02-001 - DISCARD OF WATER FILTER | CLOSED | 38-11-02-001
Planned | 12 | 33-50-21-003 - LED FPEEPMS OPERATIONAL CHECK OF LEDS FPEEPMS | CLOSED | 33-50-21-003
Planned | 13 | 32-21-00-004 - NOSE LANDING GEAR (NLG) Lubrication of NLG at all dedicated points. | CLOSED | 32-21-00-004
Planned | 14 | 32-11-00-004 - MAIN LANDING GEAR (MLG) Lubrication of MLG at all dedicated points. | CLOSED | 32-11-00-004
Planned | 15 | 27-41-01-001 - HORIZONTAL STABILIZER ACTUATOR Lubrication of Horizontal Stabilizer Actuator. With a Grease Gun, refill Ballnut with grease. | CLOSED | 27-41-01-001
Planned | 16 | 32-49-07-001 - MAIN LANDING GEAR (MLG) WHEEL TIRE CHECK MLG WHEEL TIRE FOR INFLATION PRESSURE. | CLOSED | 32-49-07-001
Planned | 17 | 52-42-51-003 - AFT SERVICE DOOR PNEUMATIC ASSEMBLY GAUGE Visual Check of pressure of the Emergency Opening Pneumatic Assembly Bottle. | CLOSED | 52-42-51-003
Planned | 19 | 52-12-51-003 - AFT PASSENGER DOOR EMERGENCY OPENING PNEUMATIC ASSEMBLY Visual Check of pressure of the Emergency Opening Pneumatic Assembly Bottle. | CLOSED | 52-12-51-003
Planned | 20 | 52-41-51-003 - FORWARD SERVICE DOOR EMERGENCY OPENING PNEUMATIC ASSEMBLY Visual Check of pressure of the Emergency Opening Pneumatic Assembly Bottle. | CLOSED | 52-41-51-003
Planned | 21 | 32-49-11-001 - BRAKE WEAR INDICATOR / BRAKE ASSEMBLY General Visual Inspection of Brake Wear Indicator and Brake Assembly. Inspect brake wear indicator pin, brakes general conditions and external hydraulic leakage. | CLOSED | 32-49-11-001
Planned | 22 | 27-51-01-004C - FLAP ACTUATOR TORQUE LIMITER Operational Check of Flap Actuator Torque Limiter. | CLOSED | 27-51-01-004C
Planned | 23 | 28-21-17-001C - ENGINE FUEL SHUTOFF VALVE Operational Check of the Engine Fuel Shutoff Valve. Check on EICAS if the valve is closing by pulling the fire handle. | CLOSED | 28-21-17-001C
Planned | 24 | 28-14-00-004C - AUX FUEL TANK AFT/FWD AIR FILTERS DISCARD OF AUX FUEL TANK AFT/FWD AIR FILTERS. | CLOSED | 28-14-00-004C
Planned | 25 | 32-49-01-001 - NOSE LANDING GEAR (NLG) WHEEL ASSEMBLY General Visual Inspection of NLG Wheel Assembly. Inspect for obvious cracks or signs of overheated, broken or missing tie bolts and missing tie bolt nuts. | CLOSED | 32-49-01-001
Planned | 26 | 32-49-03-002 - NOSE LANDING GEAR (NLG) WHEEL TIRE General Visual Inspection of NLG Wheel Tire. Inspect for damage, flat spots, tread separation and wear. CLOSED GROUP DESCRIPTION STATUS EXTERNAL TASK ORIG overheated, broken or missing tie bolts and missing tie bolt nuts. | CLOSED | 32-49-03-002
Planned | 28 | 32-49-03-001 - NOSE LANDING GEAR (NLG) WHEEL TIRE CHECK NLG WHEEL TIRE FOR INFLATION PRESSURE. | CLOSED | 32-49-03-001
Planned | 29 | 52-11-51-003 - FORWARD PASSENGER DOOR EMERGENCY OPENING PNEUMATIC ASSEMBLY Visual Check of pressure of the Emergency Opening Pneumatic Assembly Bottle. | CLOSED | 52-11-51-003
Planned | 30 | 32-49-07-002 - MAIN LANDING GEAR (MLG) WHEEL TIRE General Visual Inspection of MLG Wheel Tire. Inspect for damage, flat spots, tread separation and wear. | CLOSED | 32-49-07-002
Planned | 31 | 27-03-05-001 - FLY-BY-WIRE BACK-UP BATTERY Restoration of Fly-by-Wire Back-up Battery. PN:501-1228-04, SN: 84829 | OPEN | 27-03-05-001
Planned | 32 | 27-03-05-002 - FLY-BY-WIRE BACK-UP BATTERY Functional Check of FBW Back- up Battery Charge. PN:501-1228-04, SN: 84829 | CLOSED | 27-03-05-002
Planned | 33 | 25-63-01-001 - PORTABLE EMERGENCY LOCATOR TRANSMITTER Operational Check Portable Emergency Locator Transmitter. NOTE: REGISTER THE HEXADECIMAL CODE PN DO ELT: 01N65920, SN DO ELT:14129205 | CLOSED | 25-63-01-001
Planned | 34 | COMPLY WITH AMM TASK 49-10-00-620- 801-A - AUXILIARY POWER UNIT (APU) - PRESERVATION FOR LESS THAN 90 DAYS. - (IN CONDITIONS IN WHICH YOU CAN DO ITS TEST AT AN INTERVAL OF NO MORE THAN 30 DAYS). NOTE: THIS TASK MUST BE PERFORMED ON XXXXX XX, 20XX. | OPEN | APU PRESERVATION - 0 TO 90
Internal Procedure | 35 | COMPLY WITH GE LMM 72-00-00 STORAGE 001 TASK 72-00-00-550-801 SUBTASK 72-00-00-630-001 PARAGRAPH 6 - DESPRESERVATION PROCEDURE OF #RH ENGINE | OPEN | ENGINE DEPRESERVATION #RH
Internal Procedure | 36 | PERFORM EXTENDED DELIVERY INSPECTION AFTER HEAVY CHECK (INTERIOR/ELECTRICAL/MECHANIC) IT0404 / IT0405 / IT0406 | OPEN | 190146-003
Planned | 37 | PERFORM FINAL INSPECTION (NOTE: IT CAN ONLY BE PERFORMED BY THE QUALITY INSPECTOR) PART 145.211 (c) (1)(vii) NOTA: QLT0013 | OPEN | 190148-124
Internal Procedure | 38 | PERFORM AIRCRAFT PRELIMINARY INSPECTION IN ACCORDANCE WITH ATTACHED FORM/REALIZAR INSPEÇÃO PRELIMINAR CONFORME FORMULÁRIO ANEXO NOTE: QLT0008 | CLOSED | 190146-002
Internal Procedure | 39 | LIST AND REMOVE ALL LOOSE ITENS BEFORE THE MAINTENANCE CHECK START. AFTER CHECK INSTALL THEM IN THE ACFT/ LISTE E REMOVA TODOS OS ITENS SOLTOS ANTES DO INÍCIO DA MANUTENÇÃO. APÓS CHECK INSTALAR NA AERONAVE. | OPEN | 190146-008
Internal Procedure | 40 | REGISTER THE FLIGHT HOURS (FH) AND FLIGHT CYCLES (FC) NOTE: ATTACH COPY OF THE LOGBOOK (LAST TWO PAGES, EXCEPT FOR ACFTS ACCOMPLISHING CVA) | CLOSED | REGISTER FH AND FC
Internal Procedure | 41 | PERFORM EXTENDED RECEIVING INSPECTION BEFORE HEAVY CHECK (INTERIOR/ELECTRICAL/MECHANIC) IT348 / IT405 / IT406 CLOSED GROUP DESCRIPTION STATUS EXTERNAL TASK ORIG AIRCRAFT/REALIZAR FILMAGEM DO INTERIOR E EXTERIOR DA AERONAVE . NOTE: DURING THIS PROCEDURE, INSTALL ALL THE AIRCRAFT PROTECTIVE COVERS | CLOSED | 190146-004
Internal Procedure | 43 | EXECUTE REFUELING OF QTU/QTA AT THE END OF THE CHECK /EXECUTAR ABASTECIMENTO DO QTU/QTA NO FINAL DO CHECK | OPEN | 190148-025
Internal Procedure | 44 | EXECUTE DRAINAGE OF QTU/QTA FOR START OF THE CHECK / EXECUTAR DRENAGEM DO QTU/QTA PARA INICO DO DCHECK | CLOSED | 190148-026
Planned | 45 | 24-36-00-002 - MAIN BATTERY Restoration of Main Battery. #AFT PN:2726CH1 (5912855-01), SN: 202205616 | OPEN | 24-36-00-002
Planned | 46 | COMPLY WITH GE LMM 72-00-00 STORAGE 001 TASK 72-00-00-550-801 SUBTASK 72-00-00-620-001 UNTIL PARAGRAPHS 5.A.(1).B - SHORT-TERM PRESERVATION (PRESERVATION OF ENGINES TO BE INACTIVE FOR 0-180 DAYS MAXIMUM) OF LH ENGINE. | OPEN | PRESERVATION SHORT-TERM
Internal Procedure | 47 | AUXILIARY POWER UNIT - DEPRESERVATION | OPEN | APU DEPRESERVATION
Planned | 49 | COMPLY WITH GE LMM 72-00-00 STORAGE 001 TASK 72-00-00-550-801 SUBTASK 72-00-00-620-001 UNTIL PARAGRAPHS 5.A.(1).B - SHORT-TERM PRESERVATION (PRESERVATION OF ENGINES TO BE INACTIVE FOR 0-180 DAYS MAXIMUM) OF RH ENGINE. | OPEN | PRESERVATION SHORT-TERM
Planned | 50 | GVI OF AFT CORE COWPRESSURE RELIEF DOOR - GVI for proper position | CLOSED | GE TASK 78-30-00-200-801
Internal Procedure | 51 | INSTALL THE OUTBOARD AND INBOARD ACCESS DOORS AFTER TO INSPECTION IAW FORM ATTACHED. INSTALE OS PAINEIS DE ACESSOS DO EXTERNO E INTERNO APOS OK DE INSPECAO. | OPEN | 190148-061
Internal Procedure | 52 | REMOVE THE OUTBOARD AND INBOARD ACCESS DOORS TO INSPECTION. REMOVA PAINEIS DE ACESSOS EXTERNO E INTERNO PARA INSPECAO | CLOSED | 190148-060
Customer Report | 53 | (FINDING) DURING T/S DVDR AND CVR WAS FOUND DVDR FAILURE. NOTE: PERFORM DVDR BATTERY REPLACEMENT | OPEN
Internal Procedure | 54 | COMPLY WITH AMM 71-00-01/400 - ENGINE #01 - REMOVAL SN:994601 AND INSTALL SN: XXXX | OPEN | REMOVAL/INSTALL - ENG #01
Customer Report | 55 | COMPLY WITH GE LMM 72-00-00 STORAGE 001 TASK 72-00-00-550-801 SUBTASK 72-00-00-620-002 - LONG- TERM PRESERVATION (PRESERVATION OF ENGINES TO BE INACTIVE FOR MORE THAN 180 DAYS, UP TO A MAXIMUM OF 2 YEARS) OF #LH ENGINE #ENG LH SN:994601 | OPEN | PRESERVAÇÃO LONG-TERM
Planned | 56 | COMPLY WITH GE LMM 72-00-00 STORAGE 001 TASK 72-00-00-550-801 SUBTASK 72-00-00-630-001 PARAGRAPH 6 - DESPRESERVATION PROCEDURE OF #LH ENGINE #ENG SPAR | OPEN | ENGINE DEPRESERVATION #LH
Planned | 57 | (CUSTOMER REPORT) ARMREST OF THE AJO SEAT LOOSE. NOTES: CLIENTE SOLICITA GARATIA VIA F/LIST | OPEN
Planned | 58 | (CUSTOMER REPORT) REPLACE MAGNETS INSTALLED IN VIP SEATS. NOTES: CLIENTE SOLICITA GARATIA VIA F/LIST GROUP DESCRIPTION STATUS EXTERNAL TASK ORIG | OPEN
Planned | 59 | (CUSTOMER REPORT) VIP AREA BASEBOARD (CREW REST) PEELING OFF. | CLOSED
Planned | 60 | (CUSTOMER REPORT) WARNING LABEL ON THE FUEL LEVEL PANEL-RH 3 FADED | CLOSED
Planned | 61 | (CUSTOMER REPORT) COMPLY WITH 315080 / EMB-190 PR / 190-00277 / AOG. SERVICE: PERFORM HFEC ON THE AFT SVC DOOR. | OPEN
Planned | 62 | (CUSTOMER REPORT) GAP IN THE LH FLAP #2 FAIRING CANOE. | OPEN
Planned | 63 | (CUSTOMER REPORT) SEAT 5B BACKREST IS LOCKED IN THE UPRIGHT POSITION. | WAIT APPROVAL
Planned | 65 | (CUSTOMER REPORT) READING LIGHT FOR SEAT 4A (CREW REST) INOPERATIVE. | OPEN
Planned | 66 | (FINDING) IT WAS FOUND THE FWD SERVICE DOOR WITH LOW PRESSURE PRESSURE 1.950 PSI IN THE PNEUMATIC ASSEMBLY. | CLOSED | 52-41-51-003 | 20
Planned | 69 | (CUSTOMER REPORT) DO THE SUBTASK GE 72-00-00-760-047 TO PERFORMANCE DATA COLLECTION OF THE ENGINE LH TO SENT TO GE | CLOSED
Planned | 70 | (CUSTOMER REPORT) CAS MESSAGE "AUTO THROTTLE FAIL" | OPEN
Planned | 71 | (CUSTOMER REPORT) MSG "TCAS FAIL" IN PFD/MFD INTERMITTENT | OPEN
Planned | 73 | (CUSTOMER REPORT) CRACK IN THE MIRROR OF PR TOILET | OPEN
Planned | 74 | (FINDING) DURING THE FUCTIONAL TEST OF THE EMERGENCY LIGHT POWER UNIT, IT WAS VERIFIED THE FAILURE MESSAGES ON THE CMC THAT ARE "EMER LT BATT MID LH/RH FAULT AND EMERG LT BATT(FWD LH)/ WR FAULT , AND THE CAS MESSAGE SHOW EMER LH BATT FAULT | OPEN | 33-50-01-001 | 3
Planned | 75 | (CUSTOMER REPORT) DURING T/S OF THE ITEM INTERNET INOP" HGA ANTENNA FAILURE WAS VERIFIED | OPEN
Planned | 76 | (FINDING) DURING TEST OF FLAP LIMITER ACTUATOR IT WAS FOUND ACESS 1431DL AND 1441FR WITH WEAR SCREWS AND MISSING WASHERS. | OPEN | 27-51-01-004C | 22
Planned | 77 | (FINDING) DURING FLAP TORQUE LIMITER FUNCTIONAL TEST FOUND TRACK 532BB FOUND CRACK ON PAD OUTBOARD. SEE REFER MANUAL ACFT PP-ADV SRM 57-58-25 REPAIR 51 | OPEN | 27-51-01-004C | 22
Planned | 78 | (FINDING) DURING FLAP TORQUE LIMITER CHECK IT WAS FOUND CRACK ON FLAP TRACK 633BB PAD INBOARD. SEE REFER MANUAL ACFT PP-ADV SRM 57-58-25 REPAIR 51 | OPEN | 27-51-01-004C | 22
Planned | 79 | (COSTUMER REQUEST) REMOVE ENGINE DRIVE PUMP FROM ENGINE PN EBUCF34-10E6A1G07 SN 994601 TO INSTAL ON ENGINE PN EBUCF34- 10E6A1G07 SN 994751. ( AS REF Task 29-11-01-000-801-A AND TASK 29-11-01- 400-801-A) | OPEN | REMOVAL/INSTALL - ENG #01 | 54
Planned | 80 | (CUSTOMER REQUEST) COMPLY REMOVAL OF INTEGRATED DRIVE GENERATOR FROM ENGINE PN EBUCF34-10E6A1G07 SN 994601 TO INSTAL ON ENGINE PN EBUCF34- 10E6A1G07 SN 994751 (REF TASK 24-21- 01/400) GROUP DESCRIPTION STATUS EXTERNAL TASK ORIG SN 994601 TO INSTAL ON ENGINE PN EBUCF34-10E6A1G07 SN 994751. ( REF TASK 26-11-01-000-801-A AND TASK 26- 11-01-400-801-A) | OPEN | REMOVAL/INSTALL - ENG #01 | 54
Planned | 82 | (FINDING) DURING REMOVE OF ACCESS 148AZ AFT BULKHEAD AUXILIARY IT WAS FOUND MISSING WASHER AND DAMAGED SCREWS (REF AIPC: 50-32-03 ITEM: 30, 140, 190) | OPEN | 190148-060 | 52
Planned | 83 | (CUSTOMER REQUEST) COMPLY REMOVAL OF HIGH STAGE BLEED CHECK VALVE FROM ENGINE PN EBUCF34-10E6A1G07 SN 994601 TO INSTAL ON ENGINE PN EBUCF34- 10E6A1G07 SN 994751 (REF TASK 36-11- 01/400). | OPEN | REMOVAL/INSTALL - ENG #01 | 54
Planned | 84 | (CUSTOMER REQUEST) COMPLY REMOVAL OF ANTI ICE VALVE AND DUCT FROM ENGINE PN EBUCF34- 10E6A1G07 SN 994601 TO INSTAL ON ENGINE PN EBUCF34-10E6A1G07 SN 994751 (REF TASK 30-21-01/400 AND TASK 30-21-03/400) | OPEN | REMOVAL/INSTALL - ENG #01 | 54
Planned | 85 | (FINDING) IT WAS FOUND BUSHINGS IN THE ARM LINK OF THE FLAP TRACK ZONE 532BB AND 533BB WITH WEAR. | OPEN | 190148-060 | 52
Planned | 86 | (CUSTOMER REQUEST) COMPLY WITH REMOVAL OF IDG OIL COOLER FROM ENGINE PN EBUCF34-10E6A1G07 SN 994601 TO INSTAL ON ENGINE PN EBUCF34-10E6A1G07 SN 994751 (REF LMM TASK 75-33-00-050-801). | OPEN | REMOVAL/INSTALL - ENG #01 | 54
Planned | 87 | (FINDING) IT WAS FOUND BUSHINGS IN THE ARM LINK OF THE FLAP TRACK ZONE 632BB WITH WEAR. | OPEN |  | 62
Planned | 88 | (CUSTOMER REQUEST) COMPLY WITH REMOVAL OF NAPRSOV AND DUCT FROM ENGINE PN EBUCF34-10E6A1G07 SN 994601 TO INSTAL ON ENGINE PN EBUCF34-10E6A1G07 SN 994751.(Task 36-11-03-000-801-A AND TASK 36-11-03- 400-801-A). | OPEN | REMOVAL/INSTALL - ENG #01 | 54
Planned | 89 | (CUSTOMER REQUEST ) COMPLY WITH REMOVAL OF CENTERBODY FWD AND AFT FROM ENGINE PN EBUCF34- 10E6A1G07 SN 994601 TO INSTAL ON ENGINE PN EBUCF34-10E6A1G07 SN 994751. (REF LMM TASK 78-00-00-040- 802). | OPEN | REMOVAL/INSTALL - ENG #01 | 54
Planned | 90 | (CUSTOMER REQUEST) COMPLY I/A/W LMM 77-00-00-050-809 - OIL LEVEL REMOVAL, CLEANING, INSPECTION, AND INSTALLATION FROM ENGINE P/N EBUCF34-10E6A1G07 - S/N 994601 FOR ENGINE S/N 994751 . | OPEN | REMOVAL/INSTALL - ENG #01 | 54
Planned | 91 | (CUSTOMER REQUEST) COMPLY WITH REMOVAL OF LOW STAGE BLEED CHECK VALVE FROM ENGINE PN EBUCF34-10E6A1G07 SN 994601 TO INSTAL ON ENGINE PN EBUCF34- 10E6A1G07 SN 994751 ( REF AMM TASK 36-11-02/400). | OPEN | REMOVAL/INSTALL - ENG #01 | 54
Planned | 92 | (CUSTOMER REQUEST) COMPLY I/A/W LMM TASK 76-00-00-050-804 FADEC REMOVAL, CLEANING, INSPECTION AND INSTALLATION FROM ENGINE P/N EBUCF34-10E641G07 - S/N 994601 FOR ENG P/N EBUCF34-10E641G07 S/N 994751. | OPEN | REMOVAL/INSTALL - ENG #01 | 54
Planned | 93 | (CUSTOMER REQUEST) COMPLY WITH REMOVAL OF LPTACC VALVE FROM ENGINE PN EBUCF34-10E6A1G07 SN 994601 TO INSTAL ON ENGINE PN EBUCF34-10E6A1G07 SN 994751 (REF TASK 75-23-02-000-801-A) GROUP DESCRIPTION STATUS EXTERNAL TASK ORIG | OPEN | REMOVAL/INSTALL - ENG #01 | 54
Planned | 94 | (CUSTOMER REQUEST) COMPLY WITH REMOVAL OF CENTER BODY FROM ENGINE PN EBUCF34-10E6A1G07 SN 994601 TO INSTAL ON ENGINE PN EBUCF34-10E6A1G07 SN 994751 ( REF LMM TASK 78-00-00-040-801 ). | OPEN | REMOVAL/INSTALL - ENG #01 | 54
Planned | 95 | (CUSTOMER REQUEST) COMPLY WITH REMOVAL OF EXHAUST NOZZLE FROM ENGINE PN EBUCF34-10E6A1G07 SN 994601 TO INSTAL ON ENGINE PN EBUCF34-10E6A1G07 SN 994751 (REF TASK 78-00-00-040-803 ). | OPEN | REMOVAL/INSTALL - ENG #01 | 54
Planned | 96 | (CUSTUMER REQUEST) COMPLY REMOVAL OF THE ENG FIREWALL LH/RH AND CLOSURE P/N: EBUCF34- 10E6A1G07 S/N: 994601 TO INSTALL ON ENGINE P/N: EBUCF34-10E6A1G07 S/N: 994751 (REF. AMM 71-30-02/400) | OPEN | REMOVAL/INSTALL - ENG #01 | 54
Planned | 97 | (CUSTUMER REQUEST) COMPLY REMOVAL OF THE ENG HARNESS W9B (ACCELEROMETER) P/N: EBUCF34- 10E6A1G07 S/N: 994601 TO INSTALL ON ENGINE P/N: EBUCF34-10E6A1G07 S/N: 994751 (REF. AMM 71-50-04/400). | OPEN | REMOVAL/INSTALL - ENG #01 | 54
Planned | 98 | (CUSTUMER REQUEST) COMPLY REMOVAL OF THE ENG FAN COWLS HOLD OPEN RODS P/N: EBUCF34- 10E6A1G07 S/N: 994601 TO INSTALL ON ENGINE P/N: EBUCF34-10E6A1G07 S/N: 994751 (REF. AMM 71-15-01/400). | OPEN | REMOVAL/INSTALL - ENG #01 | 54
SB/ADs | 20000 | COMPLY WITH AD (ANAC) 2023-11-02 - PARAGRAPHS (B) UNTIL (G) - KIDDE AEROSPACE & DEFENSE OVERHEAT DETECTION SYSTEM (ODS) SENSING ELEMENTS - QUALITY ESCAPE | OPEN | AD (ANAC) 2023-11-02